SCOPE CHANGE DOCUMENT

M9: Enterprise UI (FEAT-02)

Complete Milestone Redesign & Sprint Planning

| Project: | myAgentic-IT-Project-team-V2 |
| --- | --- |
| Repository: | github.com/RobertAgterhuis |
| Branch: | main |
| Date: | March 13, 2026 |
| Milestone: | M9 (#37) |
| Priority: | P1-high (elevated from P2-medium) |

# 1. Executive Summary

This document replaces the current M9: Enterprise UI (FEAT-02) milestone (GitHub milestone #37) and its single issue (#197) with a comprehensive, requirement-aligned scope that addresses five critical gaps identified through deep code analysis of the main branch. The original milestone contained only one generic epic with 7 abstract stories and 24 story points. This scope change expands M9 into 8 focused sprints containing 42 detailed issues totalling approximately 168 story points, reflecting the true complexity of delivering a production-grade enterprise UI.

# 2. Current State Analysis

## 2.1 Codebase Statistics

| File / Area | Lines / Detail |
| --- | --- |
| index.html (main UI) | 4,909 lines — monolithic single file |
| design-system.css | 3,485 lines — external stylesheet |
| dashboard.js | 1,391 lines — dashboard rendering module |
| dashboard.html | 882 lines — dashboard template |
| landing.html | 440 lines — marketing landing page |
| API routes (11 modules) | 30+ REST endpoints (GET/POST/PUT/PATCH/DELETE) |
| Backend (server + models + store) | 1,726 lines across server.js, models.js, store.js |
| Total frontend code | ~11,100 lines of vanilla JS/HTML/CSS |
| Test coverage | 1,172 tests (363 Jest + 809 Vitest), 70%+ enforced |

## 2.2 Critical Findings

### Finding 1: No UI Framework — Vanilla JavaScript Throughout

The entire frontend is built with raw vanilla JavaScript. The index.html file alone contains 237+ direct DOM manipulation calls (innerHTML, textContent, appendChild, createElement, classList, querySelector). There is no component model, no reactivity system, no virtual DOM, and no state management library. All UI state is managed through global variables in a single IIFE scope.

### Finding 2: Monolithic Architecture — GOD Files

The index.html file (4,909 lines) is a single monolithic file containing inline CSS (~1,100 lines of design tokens and theme variables), HTML structure, and embedded JavaScript (~3,700 lines). This directly violates the project's own mandatory code requirements (DRY, No GOD code, Modular). The design-system.css file (3,485 lines) partially duplicates and partially conflicts with the inline CSS variables in index.html.

### Finding 3: No Storybook — Only Planning Documents

Despite the storybook-agent (agent #31) having produced a component inventory and setup report, zero Storybook infrastructure exists in the codebase. There are no .stories files, no Storybook configuration (.storybook/ directory), no Storybook devDependencies in package.json, and no npm scripts to launch Storybook. The component inventory document lists 11 components (Button, InputField, Badge, Card, AlertBanner, FormRow, TopNavigation, SidePanel, ModalDialog, SprintBoardTemplate, RiskDashboardPage) but none are implemented as isolated, reusable components.

### Finding 4: Emoji-Based Icons — No Icon Library

All icons throughout the UI are Unicode emoji characters (e.g., &#128203; for clipboard, &#128260; for refresh, &#128229; for export, &#128640; for rocket, &#9878; for law). These render inconsistently across operating systems and browsers, are not accessible by default, cannot be styled (color, size, weight), and look unprofessional in an enterprise context.

### Finding 5: Partial API Integration

The backend exposes 30+ REST API endpoints across 11 route modules (questionnaires, decisions, commands, progress, drift, metrics-dashboard, dashboard, milestones, subscribe, orchestrator, misc). However, the frontend only actively consumes a subset of these. Several endpoint groups are completely unused by the UI, including drift detection (GET /api/drift), metrics flush (POST /api/metrics/flush), session export (GET /api/session), milestone templates (full CRUD), and the advanced orchestrator endpoints (advance, recover, sprint-gate, validate-gate).

### Finding 6: Design Token Duplication and Drift

There are three separate sources of design tokens that are partially inconsistent with each other: (1) docs/brand/design-tokens.json — the canonical source with 8 token categories; (2) index.html inline :root CSS variables using an indigo/violet palette (#6366f1); (3) design-system.css :root variables using a navy/orange enterprise palette (#0A3A66, #E87722). These systems define different primary colors, different spacing scales, and different typography stacks.

### Finding 7: No Localization Integration in UI

Locale files exist in three languages (en-US, de-DE, fr-FR) with ui-labels.json, validation-messages.json, and doc-snippets.json. However, the index.html frontend uses hardcoded English strings in a STRINGS object rather than loading from the locale system. The i18n infrastructure is present in the backend (Weblate sync scripts) but disconnected from the frontend.

# 3. Requirements Gap Analysis

The following table maps each stated requirement against the current implementation status and the gap that must be closed.

| Requirement | Current State | Gap | Effort |
| --- | --- | --- | --- |
| Complete Storybook-driven design system | Planning docs only (component-inventory.md, storybook-setup-report.md). Zero Storybook infrastructure. | Full Storybook 8.x setup, 40+ stories across atomic design layers, CI integration | ~34 story points across 2 sprints |
| Best UI framework for complete UI | Vanilla JS with 237+ direct DOM manipulations. No component model. | Framework selection, migration from vanilla JS, component architecture | ~28 story points across 2 sprints |
| Best fitting icon library | Unicode emoji characters throughout. Inconsistent rendering, unstyled. | Icon library selection, 60+ icon replacements, accessibility audit | ~8 story points in 1 sprint |
| Exceptional UX and UI feedback | Basic toasts exist. No loading states, skeleton screens, optimistic updates, or error boundaries. | Toast system redesign, loading/skeleton/empty states, confirmation dialogs, progress indicators | ~21 story points across 2 sprints |
| Complete API integration (POST/PUT/GET/PATCH) | ~40% of API endpoints consumed. Milestone CRUD, drift, templates, advanced orchestrator unused. | Full REST integration, real-time SSE, optimistic mutations, error recovery | ~34 story points across 2 sprints |

# 4. UI Framework Recommendation

Given the project constraints (Node.js 18+ runtime, zero runtime dependency philosophy, existing vanilla JS codebase, enterprise context, Storybook requirement), the following three frameworks were evaluated:

## 4.1 Option A: React 18 + Vite (RECOMMENDED)

Rationale: React is the strongest choice for this project for several interconnected reasons. First, the existing Storybook setup report already recommends React + Vite, making it the path of least resistance. Second, React's component model maps directly to the 11-component atomic design inventory already documented. Third, React has the most mature Storybook integration (@storybook/react-vite) with first-class support for all required addons (a11y, interactions, viewport). Fourth, the enterprise ecosystem (shadcn/ui, Radix, Tanstack Query, Tanstack Table) provides production-ready components that match the dashboard, table, and form requirements. Fifth, React's declarative rendering eliminates the 237+ imperative DOM manipulation calls, solving the GOD-file problem architecturally. Sixth, the Vite bundler provides hot module replacement during development while producing optimized static builds for production, maintaining the 'zero external runtime dependency' philosophy for the deployed server (the Node.js server serves the built static files).

| Attribute | Detail |
| --- | --- |
| Framework | React 18.3+ with TypeScript |
| Build tool | Vite 6.x (fast HMR, optimized production builds) |
| Component library | shadcn/ui (Radix primitives + Tailwind CSS) |
| State management | Tanstack Query (server state) + Zustand (client state) |
| Data tables | Tanstack Table v8 (headless, accessible) |
| Storybook | Storybook 8.x with @storybook/react-vite |
| Accessibility | Radix primitives (WCAG 2.1 AA built-in) |
| Testing | Vitest + React Testing Library + Storybook interactions |
| Pros | Largest ecosystem, best Storybook support, TypeScript-first, matches existing docs |
| Cons | Bundle size overhead (~45KB gzipped), learning curve for team unfamiliar with React |

## 4.2 Option B: Vue 3 + Vite

Rationale: Vue 3 with the Composition API offers a gentler migration path from vanilla JS due to its template syntax being closer to HTML. Vue's Storybook support (@storybook/vue3-vite) is mature though slightly behind React. Vue's smaller bundle size (~33KB gzipped) aligns well with the 'zero dependency' philosophy. However, the enterprise component ecosystem (PrimeVue, Vuetify 3) is less mature than React's shadcn/ui, and the existing Storybook planning docs explicitly recommend React. Vue would require rewriting the storybook-setup-report recommendations.

## 4.3 Option C: Svelte 5 + SvelteKit

Rationale: Svelte 5 with runes produces the smallest bundle size (~2KB runtime) and compiles to vanilla JS, which philosophically aligns with the project's 'zero runtime dependency' stance. However, Svelte's Storybook support is still in community-maintained state without official first-party backing. The enterprise component ecosystem (Skeleton UI, shadcn-svelte) is nascent. The testing story (Svelte Testing Library) is less battle-tested for large applications. This makes Svelte a higher-risk choice despite its performance advantages.

## 4.4 Recommendation Summary

| Criterion | Weight | React | Vue | Svelte |
| --- | --- | --- | --- | --- |
| Storybook integration | 30% | 10/10 | 8/10 | 5/10 |
| Enterprise components | 25% | 10/10 | 7/10 | 5/10 |
| Existing doc alignment | 15% | 10/10 | 4/10 | 3/10 |
| Bundle size / perf | 10% | 7/10 | 8/10 | 10/10 |
| Accessibility built-in | 10% | 9/10 | 7/10 | 6/10 |
| Migration effort | 10% | 7/10 | 8/10 | 6/10 |
| WEIGHTED TOTAL | 100% | 9.2 / 10 | 6.9 / 10 | 5.4 / 10 |

Verdict: React 18 + Vite + shadcn/ui is the recommended stack. It scores highest on the two most critical dimensions (Storybook integration and enterprise component availability) while aligning perfectly with the existing Storybook planning documents.

# 5. Icon Library Recommendation

The project currently uses Unicode emoji characters for all icons. The recommended replacement is:

## 5.1 Recommended: Lucide React

Lucide is an open-source icon library (MIT licensed) that provides 1,500+ icons as tree-shakeable React components. It is the successor to Feather Icons and is the default icon library used by shadcn/ui, making it the natural pairing with the recommended UI framework stack.

| Attribute | Detail |
| --- | --- |
| Library | lucide-react (tree-shakeable React components) |
| Icon count | 1,500+ icons covering all enterprise UI needs |
| Bundle impact | ~300 bytes per icon (tree-shaken), zero impact for unused icons |
| Customization | Full CSS control: color, size, strokeWidth via props or className |
| shadcn/ui alignment | Default icon library for shadcn/ui; zero configuration needed |
| Accessibility | Built-in aria-hidden by default; pair with sr-only labels for meaning |
| Alternatives considered | Phosphor Icons (similar quality, less shadcn integration), Heroicons (Tailwind-native but smaller set), Material Symbols (heavier, Google ecosystem) |

# 6. Revised Milestone Definition

## 6.1 Original vs. Revised Scope

| Attribute | Original (Issue #197) | Revised |
| --- | --- | --- |
| Issues | 1 epic | 42 issues across 8 sprints |
| Story Points | 24 | ~168 |
| Sprints | 1 (Sprint 9) | 8 (Sprint 9A through 9H) |
| Duration | Undefined | 16 weeks (2 weeks per sprint) |
| Due Date | Nov 29, 2026 | Nov 29, 2026 (maintained) |
| Priority | P2-medium | P1-high |
| Labels | S9, enhancement, scope-change | S9A-S9H, enhancement, P1-high, FEAT-02 |

# 7. Sprint Plan — Detailed Issue Breakdown

Each sprint is designed for a 2-week cadence. Issues are ordered by dependency and priority within each sprint. Story points follow a Fibonacci scale (1, 2, 3, 5, 8, 13). All issues inherit the mandatory code requirements (DRY, No GOD code, Modular, Best-practice folder structure).

## Sprint 9A: Foundation — Framework & Tooling Setup (Weeks 1-2)

Goal: Establish the React + Vite + TypeScript development environment, configure Storybook 8.x, and unify design tokens into a single source of truth. This sprint produces zero user-visible features but creates the foundation every subsequent sprint depends on.

| # | Issue Title | SP | Priority | Type | Label |
| --- | --- | --- | --- | --- | --- |
| 1 | Initialize React 18 + Vite 6 + TypeScript project in src/webapp/ui/ | 5 | P0 | setup | S9A, FEAT-02 |
| 2 | Configure Storybook 8.x with react-vite builder and addons (a11y, interactions, viewport, essentials) | 5 | P0 | setup | S9A, FEAT-02 |
| 3 | Unify design tokens: single design-tokens.json → CSS variables build pipeline | 5 | P0 | refactor | S9A, FEAT-02 |
| 4 | Install and configure shadcn/ui with Tailwind CSS + Radix primitives | 3 | P1 | setup | S9A, FEAT-02 |
| 5 | Install Lucide React icon library and create icon usage guide | 2 | P1 | setup | S9A, FEAT-02 |
| 6 | Configure Vitest + React Testing Library for component testing | 3 | P1 | setup | S9A, FEAT-02 |

Sprint 9A Total: 23 story points | 6 issues

## Sprint 9B: Design System Atoms (Weeks 3-4)

Goal: Build the atomic-level design system components (Button, InputField, Badge, TextRun, Spinner, Toggle) as isolated, Storybook-documented, fully accessible React components. Each component must have stories for every state (default, hover, focus, active, disabled, loading, error).

| # | Issue Title | SP | Priority | Type | Label |
| --- | --- | --- | --- | --- | --- |
| 7 | Button component: primary, secondary, accent, danger, ghost variants + loading state | 5 | P0 | component | S9B, FEAT-02 |
| 8 | InputField component: text, email, password, search types + validation states | 5 | P0 | component | S9B, FEAT-02 |
| 9 | Badge component: success, warning, error, info, neutral variants (sm/md sizes) | 3 | P1 | component | S9B, FEAT-02 |
| 10 | Toggle/Switch component with accessible labeling and animation | 3 | P1 | component | S9B, FEAT-02 |
| 11 | Spinner and Skeleton loader atoms for loading states | 3 | P1 | component | S9B, FEAT-02 |
| 12 | Typography component set (Heading, Text, Label, Code) with token-driven scale | 2 | P1 | component | S9B, FEAT-02 |

Sprint 9B Total: 21 story points | 6 issues

## Sprint 9C: Design System Molecules & Organisms (Weeks 5-6)

Goal: Compose atoms into molecules (Card, AlertBanner, FormRow, SearchField) and organisms (TopNavigation, SidePanel, ModalDialog, DataTable). Each organism is Storybook-documented and wired to the unified design token system.

| # | Issue Title | SP | Priority | Type | Label |
| --- | --- | --- | --- | --- | --- |
| 13 | Card component: flat/raised elevation, tone variants, title/meta/actions slots | 5 | P0 | component | S9C, FEAT-02 |
| 14 | AlertBanner component: success/warning/error/info with dismissible option | 3 | P1 | component | S9C, FEAT-02 |
| 15 | FormRow molecule: label, helper text, input slot, validation error display | 3 | P1 | component | S9C, FEAT-02 |
| 16 | TopNavigation organism: project context, search, actions, status indicator | 5 | P0 | component | S9C, FEAT-02 |
| 17 | SidePanel organism: collapsible nav with phase/agent progress indicators | 5 | P0 | component | S9C, FEAT-02 |
| 18 | ModalDialog organism: sm/md/lg sizes, focus trap, return-focus, aria-modal | 5 | P0 | component | S9C, FEAT-02 |

Sprint 9C Total: 26 story points | 6 issues

## Sprint 9D: UX Feedback System & Data Components (Weeks 7-8)

Goal: Build the complete UX feedback infrastructure (toast notifications, confirmation dialogs, progress indicators, empty states, error boundaries) and the data-heavy components (DataTable with sort/filter/pagination, MetricCard, ActivityFeed).

| # | Issue Title | SP | Priority | Type | Label |
| --- | --- | --- | --- | --- | --- |
| 19 | Toast notification system: stacking, auto-dismiss, undo action, aria-live | 5 | P0 | component | S9D, FEAT-02 |
| 20 | ConfirmDialog: destructive action confirmation with customizable messaging | 3 | P1 | component | S9D, FEAT-02 |
| 21 | ProgressBar and StepIndicator for pipeline and multi-step workflows | 3 | P1 | component | S9D, FEAT-02 |
| 22 | EmptyState and ErrorBoundary components with recovery actions | 3 | P1 | component | S9D, FEAT-02 |
| 23 | DataTable organism: Tanstack Table integration, sorting, filtering, pagination, row actions | 8 | P0 | component | S9D, FEAT-02 |
| 24 | MetricCard and ActivityFeed molecules for dashboard data display | 3 | P1 | component | S9D, FEAT-02 |

Sprint 9D Total: 25 story points | 6 issues

## Sprint 9E: API Integration Layer (Weeks 9-10)

Goal: Create the complete API client layer using Tanstack Query, implementing typed hooks for every backend endpoint. This sprint introduces optimistic mutations, real-time SSE subscriptions, request deduplication, and centralized error handling. No UI page work yet — this produces the data layer that pages will consume.

| # | Issue Title | SP | Priority | Type | Label |
| --- | --- | --- | --- | --- | --- |
| 25 | Tanstack Query setup: QueryClient config, devtools, error/retry policies | 3 | P0 | setup | S9E, FEAT-02 |
| 26 | API hooks: Questionnaires (GET /api/questionnaires, POST /api/save) | 5 | P0 | integration | S9E, FEAT-02 |
| 27 | API hooks: Decisions full CRUD (GET, POST, activate-category) | 5 | P0 | integration | S9E, FEAT-02 |
| 28 | API hooks: Milestones full CRUD (GET, POST, PUT, PATCH/archive, Templates) | 5 | P0 | integration | S9E, FEAT-02 |
| 29 | API hooks: Orchestrator (status, advance, command, reset, recover, gates) | 5 | P0 | integration | S9E, FEAT-02 |
| 30 | API hooks: Dashboard (health, metrics, activity, stats), Drift, Progress, SSE events | 5 | P0 | integration | S9E, FEAT-02 |

Sprint 9E Total: 28 story points | 6 issues

## Sprint 9F: Page Assembly — Command Center & Pipeline (Weeks 11-12)

Goal: Assemble the first two complete pages by composing design system components and API hooks: the Command Center (project launch, command queue, agent status) and the Pipeline Visualization (state machine flow, gate results, activity log). Both pages must be fully functional with live API data.

| # | Issue Title | SP | Priority | Type | Label |
| --- | --- | --- | --- | --- | --- |
| 31 | App shell: React Router layout with TopNavigation, SidePanel, tab routing | 5 | P0 | page | S9F, FEAT-02 |
| 32 | Command Center page: project brief input, command queue, agent progress | 5 | P0 | page | S9F, FEAT-02 |
| 33 | Pipeline page: state machine visualization, phase flow, gate results panel | 5 | P0 | page | S9F, FEAT-02 |
| 34 | Help panel overlay: topic search, keyboard shortcut (?) trigger | 3 | P1 | page | S9F, FEAT-02 |

Sprint 9F Total: 18 story points | 4 issues

## Sprint 9G: Page Assembly — Questionnaires, Decisions, Dashboard (Weeks 13-14)

Goal: Assemble the remaining three core pages: Questionnaires (sidebar navigation, answer forms, inline save), Decisions (filter/sort, status lifecycle, bulk actions), and Dashboard Home (health cards, metric charts, activity feed, milestone table). All pages fully integrated with live API data and real-time SSE updates.

| # | Issue Title | SP | Priority | Type | Label |
| --- | --- | --- | --- | --- | --- |
| 35 | Questionnaires page: sidebar nav, phase grouping, answer forms, progress tracking | 8 | P0 | page | S9G, FEAT-02 |
| 36 | Decisions page: filter bar, status lifecycle flow, inline editing, category activation | 8 | P0 | page | S9G, FEAT-02 |
| 37 | Dashboard Home page: health cards, metric summaries, activity feed, milestone table CRUD | 8 | P0 | page | S9G, FEAT-02 |
| 38 | Metrics page: drift detection display, KPI charts, metrics dashboard integration | 5 | P1 | page | S9G, FEAT-02 |

Sprint 9G Total: 29 story points | 4 issues

## Sprint 9H: Polish, i18n, Accessibility & Launch (Weeks 15-16)

Goal: Final sprint focused on polish, production readiness, and quality gates. Integrate the locale system (en-US, de-DE, fr-FR), run full WCAG 2.1 AA accessibility audit, configure Storybook Chromatic or CI visual regression, update Docker build for the React frontend, and create the Storybook static build for documentation.

| # | Issue Title | SP | Priority | Type | Label |
| --- | --- | --- | --- | --- | --- |
| 39 | i18n integration: connect locale JSON files (en-US, de-DE, fr-FR) to React via react-intl or i18next | 5 | P1 | integration | S9H, FEAT-02 |
| 40 | WCAG 2.1 AA audit: axe-core CI gate, keyboard navigation test, screen reader validation | 5 | P0 | a11y | S9H, FEAT-02 |
| 41 | Dark mode: theme toggle integration, Storybook theme decorator, token validation | 3 | P1 | polish | S9H, FEAT-02 |
| 42 | Production build: Vite build config, Docker update, Storybook static export, CI pipeline update | 5 | P0 | devops | S9H, FEAT-02 |

Sprint 9H Total: 18 story points | 4 issues

# 8. Total Scope Summary

| Sprint | Focus Area | Issues | Points | Weeks |
| --- | --- | --- | --- | --- |
| S9A | Foundation: Framework & Tooling Setup | 6 | 23 | 1-2 |
| S9B | Design System Atoms | 6 | 21 | 3-4 |
| S9C | Design System Molecules & Organisms | 6 | 26 | 5-6 |
| S9D | UX Feedback System & Data Components | 6 | 25 | 7-8 |
| S9E | API Integration Layer (All Endpoints) | 6 | 28 | 9-10 |
| S9F | Page Assembly: Command Center & Pipeline | 4 | 18 | 11-12 |
| S9G | Page Assembly: Questionnaires, Decisions, Dashboard | 4 | 29 | 13-14 |
| S9H | Polish, i18n, Accessibility & Launch | 4 | 18 | 15-16 |
| TOTAL |  | 42 | 188 | 16 |

# 9. API Endpoint Coverage Map

The following table documents every backend API endpoint and which sprint delivers its frontend integration. Endpoints marked NEW indicate they currently have no frontend consumer.

| Endpoint | Method | Status | Sprint | UI Consumer |
| --- | --- | --- | --- | --- |
| GET /api/questionnaires | GET | Exists | S9E #26 | Questionnaires page |
| POST /api/save | POST | Exists | S9E #26 | Questionnaires page |
| GET /api/decisions | GET | Exists | S9E #27 | Decisions page |
| POST /api/decisions | POST | Exists | S9E #27 | Decisions page |
| POST /api/decisions/activate-category | POST | NEW | S9E #27 | Decisions page |
| GET /api/milestones | GET | Exists | S9E #28 | Dashboard page |
| POST /api/milestones | POST | Exists | S9E #28 | Dashboard page |
| GET /api/milestones/:id | GET | NEW | S9E #28 | Dashboard detail |
| PUT /api/milestones/:id | PUT | Exists | S9E #28 | Dashboard page |
| PATCH /api/milestones/:id/archive | PATCH | Exists | S9E #28 | Dashboard page |
| Milestone Templates (POST/GET/DELETE/apply) | CRUD | NEW | S9E #28 | Dashboard page |
| GET /api/orchestrator/status | GET | Exists | S9E #29 | Pipeline page |
| POST /api/orchestrator/command | POST | Exists | S9E #29 | Command Center |
| POST /api/orchestrator/advance | POST | NEW | S9E #29 | Pipeline page |
| POST /api/orchestrator/validate-gate | POST | NEW | S9E #29 | Pipeline page |
| POST /api/orchestrator/sprint-gate | POST | NEW | S9E #29 | Pipeline page |
| POST /api/orchestrator/reset¦recover¦error | POST | NEW | S9E #29 | Pipeline page |
| Dashboard (health/metrics/activity/stats) | GET | Exists | S9E #30 | Dashboard page |
| GET /api/drift | GET | NEW | S9E #30 | Metrics page |
| GET /api/progress | GET | Exists | S9E #30 | Pipeline + nav |
| GET /api/events (SSE) | GET | Exists | S9E #30 | Global real-time |
| GET /api/metrics/dashboard | GET | NEW | S9E #30 | Metrics page |

# 10. Migration Strategy

The migration from the current vanilla JS UI to React follows a strangler-fig pattern to avoid a risky big-bang rewrite:

Phase 1 (Sprint 9A-9D): Build the new React application in src/webapp/ui/ as a parallel codebase. The existing index.html continues to serve as the production UI during this phase. All design system components are built and validated in Storybook independently.

Phase 2 (Sprint 9E): Create the API integration layer as React hooks. These hooks are tested against the running Node.js server using msw (Mock Service Worker) for unit tests and real API calls for integration tests.

Phase 3 (Sprint 9F-9G): Assemble complete pages in the React app. Each page is feature-flagged. When a React page reaches parity with its vanilla JS equivalent, the route is switched over. This allows incremental migration without downtime.

Phase 4 (Sprint 9H): Remove the old index.html, update Docker configuration to serve Vite-built static files, and run final accessibility and performance audits. The Storybook static build is published alongside the application.

# 11. Risks & Mitigations

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Scope exceeds 16-week window | High | Medium | Sprints 9G-9H can be trimmed; Metrics page (issue #38) is P1, not P0 |
| React learning curve slows early sprints | Medium | Medium | shadcn/ui provides pre-built components; Storybook enables isolated development |
| Design token conflicts during migration | Medium | High | Sprint 9A explicitly unifies tokens before any component work begins |
| Backend API changes break frontend | High | Low | TypeScript API types + Tanstack Query error boundaries + contract tests |
| Accessibility regression during migration | High | Medium | Storybook a11y addon + axe-core CI gate + Radix primitives (ARIA built-in) |

# 12. Actions Required

12.1 Close existing issue #197 (S9: Enterprise UI Redesign Epic) as 'not planned' with reference to this scope change document.

12.2 Create 8 new sprint labels: S9A, S9B, S9C, S9D, S9E, S9F, S9G, S9H.

12.3 Create 42 new issues as detailed in Section 7, assigning each to milestone M9 (#37) with the corresponding sprint label.

12.4 Update milestone M9 description to reference this scope change document.

12.5 Elevate milestone M9 priority from P2-medium to P1-high.

12.6 Update the project board to reflect the 8-sprint structure.

# 13. Approval

| Role | Name / Signature | Date |
| --- | --- | --- |
| Project Owner |  |  |
| Technical Lead |  |  |

End of Scope Change Document — M9: Enterprise UI (FEAT-02)